## Sheet1
|  | Student Name: | Grant Buchanan
|  | Faculty: | Mike Panitz
|  | Mentor: | Mike Panitz
|  | Capstone Project | DDapp
Date | Hours | Task | Summary of Tasks Performed, Accomplishments, and activities
2021-04-25 | 2 | Template activity | initial template activity created with two fragments
2021-04-30 | 4 | Template recycview | template recyclerview code added
2021-05-04 | 4 | Recyclerview layout | recyclerview basic functionality added
2021-05-10 | 1 | Recyclerview layout | recyclerview UI cleaned up
2021-05-16 | 3 | Details view | groundwork for details view, details fragment added
2021-05-17 | 2 | Details view | fragment manager and adapter tweaked for details view
2021-05-18 | 5 | Details view | details view implementation finished
2021-05-29 | 5 | Room DB | room DB version 1 implemented
2021-06-01 | 4 | Room DB | room DB version 2 implemented
2021-06-07 | 6 | Recyclerview DB | DB set up for integeration to recyclerview, templates removed
2021-06-09 | 7 | Recyclerview DB | DB to recyclerview connection finished
2021-06-09 | 3 | Recyclerview DB | room DB version 3 implemented